## Sheet1
Software bug report
Project name: | Movie Theater Project
Bug ID | Title/Summary | Issue type | Classification | Environment | Step-by-step | Expected result | Actual result | Link | Attachment | Frequency | Severity | Priority | Source | Notes/Comments | Reporter | Assignee | Reported on | Due date | Date closed | Time logged | Resolution
Bug_001 | App user does not automatically update new movies when showtimes are updated | Bug | UI/Usability | Chip: Snapdragon 835 RAM: 8 GB Storage: 128 GB | 1.Open admin system. 2.Select the schedule function. 3.Enter movie id, room id and showtime. 4.Click add button. 5.Open app user. 6.Click on the upcoming button. 7.Click on movie in the list. | Show selected movie information | Movie not showing on user app |  | @ [type @ to add] | Always | Critical | High | Internal | [Additional notes or comments regarding the issue] | Tuấn | @ | 31/7/2024 | @ | @ | 16:00 | [Describe how the issue was resolved for future reference]
Bug_002 | After deleting the registrant information from the database, the user can register a new account using the deleted email information. | Bug | UI/Usability | Chip: Snapdragon 835 RAM: 8 GB Storage: 128 GB | 1.Delete user information on database by given email. 2.Open app. 3.Select the menu icon in the right corner of the app.. 4.Selects the registration function on the main interface of the system. 5.Fill in the information according to the form. 6.Click Register button. | Show successful registration message and transfer to login interface | The system notifies that the account already exists. |  | @ [type @ to add] | Always | Critical | High | Internal | [Additional notes or comments regarding the issue] | Tuấn | @ | 31/7/2024 | @ | @ | 16:00 | [Describe how the issue was resolved for future reference]
Issue type |  |  | Classification | [7 empty] | Severity
Bug | 2 |  | Security | 0 | [6 empty] | Minor | 0
Suggestion | 0 |  | Performance | 0 | [6 empty] | Medium | 0
New feature | 0 |  | UI/Usability | 2 | [6 empty] | Major | 0
|  |  | Syntax | 0 | [6 empty] | Critical | 2
|  |  | Crash | 0